## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Helping Hands For Daily Needs |  | 37 | 2021-08-21 | 2021-09-26 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-21 | 2021-08-22 | 2 days
1.2 | Finish webpage | 2021-08-23 | 2021-08-24 | 2 days
1.3 | Project Design | 2021-08-25 | 2021-08-26 | 2 days
2 | Coding
2.1 | Phase 1 | 2021-08-27 | 2021-09-05 | 10 days
2.2 | Phase 2 | 2021-09-06 | 2021-09-10 | 5 days
2.3 | Additional Features | 2021-09-10 | 2021-09-10 | 1 day
3 | Testing
3.1 | Phase 1 Testing | 2021-09-11 | 2021-09-12 | 2 days
3.2 | Modification /Any changes | 2021-09-16 | 2021-09-19 | 4 days
3.3 | Phase 2 Testing | 2021-09-20 | 2021-09-21 | 2 day
3.4 | Modification /Any changes | 2021-09-22 | 2021-09-23 | 1 day
3.5 | Final Testing | 2021-09-24 | 2021-09-24 | 1 day
4 | Documentation
4.1 | User Guide | 2021-09-25 | 2021-09-25 | 1 day
4.2 | Presentation | 2021-09-26 | 2021-09-27 | 2 days

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team leader
| Member Name | Pranav Mohan Joshi
| PRN No | 210543181074
| Description | backend - Added dependencies,java classes and interfaces with package names
2 | Role | Team member
| Member Name | Asawari Manik Kamble
| PRN No | 210543181010
| Description | backend-created java classes,interfaces and application properties.
3 | Role | Team member
| Member Name | Nayan Uttam Dongare
| PRN No | 210543181024
| Description | frontend- created jsp pages and inserted imgaes into project
4 | Role | Team member
| Member Name | Sakshi Vednath Choudhari
| PRN No | 210543181088
| Description | frontend-created jsp pages and added required bootstrap,css files